## Unified Gap Matrix
UNIFIED IMPLEMENTATION PLAN: HaseebOS v15 + TMCAI Merged Analysis
Merged from vscode-analysis (20 gaps, code-level precision) + cowork-analysis (37 gaps, implementation roadmap) into one canonical plan
# | Gap Area | Category | Status | HaseebOS v15 Spec | TMCAI Current State | Scope | Priority | Effort | Code References | Implementation Target
ARCHITECTURE & EVENT BACKBONE
1 | Pub/Sub Event Bus | Architecture | ❌ MISSING | 4 topics (feed.raw, openitems.scored, actions.approved, steering.snapshot) + 4 DLQs, ordering keys per entity, exponential backoff (1/10/60/300s), max 5 retries | setInterval loops in server.ts:16-49 for background work; node-cron in agentScheduler.ts; no @google-cloud/pubsub in package.json; process crash = lost jobs | Rebuild | P0 Critical | High | server/src/server.ts:16-49, agents/agentScheduler.ts | GCP Pub/Sub: 4 topics + 4 DLQs + push subscriptions; new server/src/middleware/pubsubHandler.ts; refactor all async paths to pub/sub
2 | ADK Agent Framework (7 Agents) | Architecture | ❌ MISSING | 7 named agents on Vertex AI Agent Engine: Brain Orchestrator (Gemini 3.1 Pro, 14 tools) + 6 workers on Flash (8-42 tools each); transfer_to_agent() delegation; 98 total tools | In-process node-cron scheduler; agentFrameworkService.ts = user-defined agents; agentExecutionEngine.ts = runs prompt through provider; agentToolService.ts = flat tool registry; all in single Node process | Rebuild | P0 Critical | High | server/src/agents/ (4 files: framework, engine, tools, conversation) | New server/src/services/adk/ with agentRegistry.ts, brainOrchestrator.ts, baseAgent.ts; Cloud Run agent worker service; tenant-scoped dispatch
3 | Tool Taxonomy (98 tools) | Architecture | 🟡 PARTIAL | 98 tools distributed across 7 agents; Brain Pro: 14, workers: 8-42 each; strict per-agent scoping | agentToolService.ts has single flat registry, no per-agent scoping; ad-hoc tool list | Rebuild | P1 High | High | server/src/agents/agentToolService.ts | Re-scope existing tools to 7-agent topology; add missing tools; depends on G2
4 | Global Trace IDs | Architecture | 🟡 PARTIAL | Trace ID propagated across Pub/Sub messages; full causal chain tracking | requestIdMiddleware.ts generates X-Request-Id per HTTP request via AsyncLocalStorage; OTel SDK installed but no message attribute wiring | Extend | P2 Medium | Low | server/src/middleware/requestId.ts | Add traceId to Pub/Sub message attributes; blocked by G1
FEED & OPEN ITEMS LAYER
5 | Event-Driven Feed Ingestion | Feed Layer | ❌ MISSING | All connectors emit to feed.raw topic; deduplication via content_hash; structured event schema with source_type, priority hints | Connectors (Gmail, WhatsApp, Drive, Calendar) sync via direct DB writes + setInterval polling; no event emission; no dedup | Rebuild | P0 Critical | High | server/src/services/gmail/, whatsapp/, drive/, calendar/ | New feedIngestionService.ts, feedDeduplicator.ts; modify connectors to publish events; feed_events DB table with content_hash index
6 | Open Items Scoring & Enrichment | Open Items | 🟡 PARTIAL | Probabilistic priority scoring, archetype classification (6 types), deduplication, entity enrichment, source correlation | openItemsService exists; priorityScoringService.ts exists; free-text type field (no enum archetypes); no dedup_hash; no shadow_score | Extend | P0 Critical | Medium | server/src/services/openItemsService.ts, priorityScoringService.ts | Extend open_items table with priority_score, dedup_hash, enrichment_data, shadow_score; add archetype enum (G17)
7 | Archetype Classification | Open Items | 🟡 PARTIAL | 6 archetypes: reply_needed, delegate, inform_only, schedule_meeting, review_risk, acknowledge | OpenItem.type is free-text in Prisma; no classifier service for archetype assignment | Extend | P1 High | Low | prisma/schema.prisma (OpenItem model) | Add enum type; Brain agent classifies on ingestion
8 | Entity Resolution Alignment | Open Items | ⚠ MISLABEL | 5 kinds: person, company, project, deal, objective | 6 kinds: contact, account, project, opportunity, risk, okr; semantic overlap (person↔contact, company↔account, deal↔opportunity, objective↔okr); spec drops risk | Rename/Align | P2 Medium | Low | prisma/schema.prisma (Entity model) | Alias or rename; decide: adopt spec names (breaking) or add aliases
ACTIONS LAYER
9 | Risk Gating (3-Tier) | Actions | ❌ MISSING | 3-tier: LOW auto-execute, MEDIUM confirm, HIGH human-approve; per-tenant risk_tolerance; every decision logged | No risk classification; actionExecutionService executes without gating; no approval workflow | Net New | P0 Critical | High | server/src/services/actionExecutionService.ts | New riskGatingService.ts, riskEvaluator.ts, approvalWorkflow.ts; extend user_profiles with risk_tolerance
10 | 35 Action Handlers (8 categories) | Actions | 🟡 PARTIAL | 35 handlers: communication, calendar, task, CRM, lifecycle, orchestration, brain, governance | 6-7 types: reply, delegate, schedule, close, erp, snooze, delegate_msg; hardcoded in executeInternal; comment 'In future: call actual connector services' | Extend | P0 Critical | High | server/src/services/actionExecutionService.ts:18, actionIdempotencyService.ts:18-20 | 28+ new handlers; orchestration & governance are novel; build alongside G9 (undo)
11 | Transactional Idempotency | Actions | 🟡 PARTIAL | Redis SETNX + SQL transaction; key: {tenant}:{action_type}:{entity_id}:{disambiguator}; TTL 24h Redis, 7d SQL | ActionIdempotencyLog Prisma upsert only; SHA-256 key gen ✓; 7d cleanup via schedulerService ✓; no distributed lock; no SETNX; crash between execute→store = re-execution | Extend | P0 Critical | Medium | server/src/services/actionIdempotencyService.ts | Add Redis SETNX layer; wrap in SQL transaction; keep existing call sites unchanged
12 | Kill Switch (30s SLA) | Actions | ❌ MISSING | 30-second halt; read-only mode blocks all writes; step-up auth to release; admin UI + audit log | None — no kill_switch table, no global state flag, no mutation-blocking middleware | Net New | P0 Critical | Medium | (none exists) | Redis flag kill_switch:{tenant_id}; Express middleware on all mutations; new safety/ route + UI toggle
13 | Cascading Undo | Actions | ❌ MISSING | Dependency graph + impact analysis; every action writes reverse operation + dependency edges; undo chain is all-or-nothing | None — no undo_log, no reverse-operation registry, no dependency graph; actions logged as notes only | Net New | P1 High | High | server/src/services/actionExecutionService.ts | New cascadingUndoService.ts, dependencyGraphService.ts; action_dependencies table; build with G10
14 | Circuit Breakers | Actions | 🟡 PARTIAL | Every external adapter wrapped; open after 5 failures in 60s, half-open after 30s, close after 3 successes | Agent.errorCount + runCount fields exist in Prisma; comment in agentFrameworkService.ts:5-6 'Circuit breaker (auto-pause after 3 errors)' — no implementation; no adapter wrapping | Net New | P1 High | Low | prisma/schema.prisma (Agent model), agents/agentFrameworkService.ts:5-6 | Drop in opossum library; wrap each adapter; Redis circuit:{tenant}:{agent} state
DECISION LOG & INTELLIGENCE LAYER
15 | Three-Layer Decision Log | Decisions | 🟡 PARTIAL | Layer 1: BQ append-only; Layer 2: curated training set; Layer 3: mutable operational view (Cloud SQL); CDC <60s latency | Postgres DecisionLog table (mutable); fields: userId, userDecision, isMatch, responseTimeMs, outcome; Prisma allows UPDATE; no BQ sink; bigQueryConnector.ts exists but for vector reads only | Extend | P0 Critical | Medium | prisma/schema.prisma (DecisionLog), server/src/connectors/BigQueryConnector.ts | Keep PG as Layer 3; add BQ sink for Layer 1 (Datastream CDC or dual-write); Layer 2 = filtered view
16 | Probabilistic Shadowing | Decisions | 🟡 PARTIAL | State machine: DRAFT→SHADOW(30d)→evaluation gate→ACTIVE; Golden Dataset gate: 95% LOW, 98% MEDIUM, manual HIGH; drift guard >2σ in 7d freezes promotions | shadowScoringService.ts: monthly job (1st Monday 7AM PKT); compares AI top-5 vs user actions from DecisionLog; emits ThoughtEntry report; no auto-adjust, no rule lifecycle, no Golden Dataset, no drift guard | Rebuild | P1 High | High | server/src/services/shadowScoringService.ts | Rule model with lifecycle states; golden_dataset table + Cloud Storage content; shadow_scores table; promotion evaluator; drift monitor; 30-day shadow period
17 | Memory Bank | Decisions | 🟡 PARTIAL | Vertex AI Memory Bank for cross-session learning (GA service) | memoryService.ts in-process + ContextMemory table; Postgres-backed; no Vertex integration | Rebuild | P2 Medium | Medium | server/src/services/memoryService.ts | Depends on G2 (Vertex AI); evaluate Vertex Memory Bank vs enhanced PG approach
18 | Morning Brief (10 sections) | Decisions | 🟡 PARTIAL | 06:00 PKT daily; 10 structured sections | dayBriefingService.ts exists; section count and schedule not confirmed against spec | Audit | P1 High | Low | server/src/services/dayBriefingService.ts | Audit sections vs spec; align schedule; add missing sections
STEERING WHEEL & UI
19 | Steering Wheel (5 tabs) | UI | 🟡 PARTIAL | 5 unified tabs: Brain Query, Morning Brief, Action Center, Action Execution (15 embedded interfaces), Health Check (13 components) | 10 fragmented pages: ChatPage, DayBriefPage, OpenItemsPage, BrainConfigPage, AgentsPage, ConnectorsPage, SchedulerPage, ThoughtPipelinePage, SettingsPage, AdminPage | Consolidate | P2 Medium | High | client/src/pages/ (10 page files) | Unified SteeringDashboard shell; consolidate 10→5 tabs; Action Execution = biggest UI lift (15 interfaces); decide fate of AgentsPage, SchedulerPage, ConnectorsPage, ThoughtPipelinePage
20 | KPI Dashboard & Trends | UI | ❌ MISSING | CEO-facing KPI cards, trend charts, anomaly alerts, agent activity timeline; filterable by date | No dedicated KPI dashboard; analytics scattered across admin | Net New | P2 Medium | Medium | (none exists) | New SteeringDashboard.tsx + KPICard, TrendChart components; kpi_values table; Recharts visualizations
21 | Kill Switch UI | UI | ❌ MISSING | Big red toggle in admin; confirmation modal; shows affected agents; last triggered time | None | Net New | P0 Critical | Low | (none exists) | New KillSwitch.tsx component in admin panel
22 | Risk Approval Queue | UI | ❌ MISSING | Pending MEDIUM/HIGH actions; approve/reject; risk assessment details; confidence score | None | Net New | P1 High | Medium | (none exists) | New RiskApprovalQueue.tsx page
23 | Decision Log Viewer | UI | ❌ MISSING | Filterable table; filter by agent, risk tier, confidence, date; expand for full context; CSV export | None — decisions exist in DB but no viewer | Net New | P1 High | Medium | (none exists) | New DecisionLog.tsx page
INFRASTRUCTURE, SECURITY & OPS
24 | Cloud SQL HA + PgBouncer | Infra | ❌ MISSING | Cloud SQL HA (primary+standby, auto-failover); PgBouncer transaction mode; read replica | Local Postgres 17 dev; docker-compose has pgbouncer but unused; no read-replica routing; no DATABASE_URL_REPLICA | Ops/Deploy | P1 High | Low | docker-compose.yml, server/src/config/env.ts | Deploy-time topology; Prisma config needs directUrl + pool-compatible schema; add replica routing
25 | Envelope Encryption (KMS) | Security | 🟡 PARTIAL | Per-user DEK; KEK in GCP KMS; envelope encrypt PII at rest | User.encrypted_dek field exists; envelopeEncryptionService.ts has conditional KMS path (needs GCP_PROJECT_ID); falls back to local ENCRYPTION_KEY; only handful of fields encrypted | Extend | P1 High | Low | server/src/services/envelopeEncryptionService.ts | Configure KMS key; audit full PII list; encrypt all sensitive fields
26 | Data Residency (4 regions) | Security | 🟡 PARTIAL | 4 regions: PK, AE, KSA, QA; per-region BQ dataset + storage | dataResidencyService.ts has region→dataset mapping (BQ_DATASET_PK/_AE/_SA/_QA); no runtime routing logic | Extend | P2 Medium | Low | server/src/services/dataResidencyService.ts | Add tenant→region resolver; route reads/writes per region
27 | Retention Tiers (Hot/Warm/Cold) | Infra | ❌ MISSING | Hot: Cloud SQL 12mo; Warm: BQ 3yr; Cold: GCS retention lock indefinite | No retention policy on any table; no archival jobs | Net New | P2 Medium | Medium | (none exists) | TTL logic per table; nightly archival job; GCS lifecycle rules
28 | Redis Infrastructure | Infra | ❌ MISSING | Memorystore Redis for kill switch, idempotency, circuit breakers, notification queue, rate limiting | No Redis in stack; all state in Postgres or in-memory | Net New | P0 Critical | Medium | server/package.json (no ioredis) | GCP Memorystore instance; new config/redis.ts; VPC connector
29 | Monitoring & Alerting | Infra | 🟡 PARTIAL | Custom dashboard: agent latency, Pub/Sub backlog, DLQ depth, kill switch, Redis, BQ export; 7+ alert policies | OpenTelemetry SDK installed; basic request logging; no custom dashboards or GCP-specific alerts | Extend | P1 High | Medium | server/src/instrumentation.ts | Cloud Monitoring dashboard; alert policies; structured logging with BQ archive
TMCAI AHEAD OF HASEEBOS (Keep & Leverage)
30 | Multi-Tenant SaaS Architecture | TMCAI Ahead | ✅ TMCAI AHEAD | Single-tenant personal system for one CEO | Full multi-tenant: tenant_id on 49 tables, tier/licensing, white-label, marketplace; HaseebOS needs all of this eventually | Keep | — | — | All Prisma models, tenantService, tierService, licenseService | TMCAI is the deployment vehicle; HaseebOS features become tenant-scoped layers
31 | Multi-Provider AI | TMCAI Ahead | ✅ TMCAI AHEAD | Gemini-only (3.1 Pro + Flash) | Gemini + Claude + GPT-4o + Groq + OpenRouter; smart routing per intent; fallback chains | Keep | — | — | server/src/services/geminiService, claudeService, openaiService, groqService | Keep multi-provider; make Gemini primary per spec; retain others as fallback/per-tenant option
32 | PII Masking & Content Sanitization | TMCAI Ahead | ✅ TMCAI AHEAD | Not specified in v15 | Full pipeline: piiService.ts + contentSanitizer.ts + outputSanitizer.ts; PII detection, masking, safe output | Keep | — | — | server/src/pipeline/piiService.ts, contentSanitizer.ts, outputSanitizer.ts | Keep and extend to cover agent outputs
33 | RAG Pipeline (Hybrid Search) | TMCAI Ahead | ✅ TMCAI AHEAD | Basic knowledge retrieval mentioned | Advanced: vector + TF-IDF via RRF, cross-encoder re-ranking, section retrieval, query rewriting, hybrid search | Keep | — | — | server/src/pipeline/ (13 files) | Keep; feed domain knowledge docs through existing pipeline
34 | Connector Breadth | TMCAI Ahead | ✅ TMCAI AHEAD | Gmail, Calendar, Tasks only | Gmail, WhatsApp (dual-provider), Drive, Calendar, Tasks, BigQuery, 32 connector types in registry | Keep | — | — | server/src/services/connectors/, server/src/services/gmail/ whatsapp/ drive/ | Keep all; add event emission to each for Pub/Sub (G5)
35 | White-Label & Marketplace | TMCAI Ahead | ✅ TMCAI AHEAD | Not specified | Full white-label theming + marketplace with connector installations | Keep | — | — | server/src/services/marketplace/, whiteLabel/ | Unique TMCAI differentiator; not in HaseebOS scope
OPEN QUESTIONS (Require Decision Before Implementation)
Q1 | MyOS vs HaseebOS Naming | Naming | ⚠ DECIDE | Spec says HaseebOS v15 | Codebase consistently says MyOS (MYOS.md, MyOS_Functional_Specification.md, in-file comments like 'MyOS Gap 3') | Decision | — | — | docs/MYOS.md, all service files | Rename in code? Keep MyOS internally + HaseebOS externally? Rebrand entirely?
Q2 | WhatsApp Dual-Provider | Integration | ⚠ DECIDE | Assumes official Meta Cloud API only | Both WebjsProvider (unofficial whatsapp-web.js, ToS risk) and MetaProvider (Meta Cloud API) exist | Decision | — | — | server/src/services/whatsapp/ (5 files) | Drop WebjsProvider (ToS risk/bans)? Keep for fallback? Meta-only?
Q3 | Vector Storage Strategy | Infra | ⚠ DECIDE | Implies Vertex Vector Search | DomainKnowledge, Document, Chunk, KnowledgeItem store embeddings as JSON in PG; no pgvector; no Vertex Vector Search | Decision | — | — | server/src/pipeline/vectorStore.ts, vertexVectorSearch.ts | Keep PG JSON embeddings? Migrate to pgvector? Full Vertex Vector Search?
Q4 | User-Defined Agents | Architecture | ⚠ DECIDE | Fixed 7-agent topology with defined roles | User-created agents with custom prompts, cron schedules, DB-backed; agentFrameworkService supports arbitrary agents | Decision | — | — | server/src/agents/agentFrameworkService.ts | Preserve alongside fixed 7? Drop? Convert to 'custom worker' agent type?
Q5 | Existing MyOS Roadmap Alignment | Architecture | ⚠ DECIDE | HaseebOS v15 spec defines its own feature set | MyOS has 3-phase roadmap (F1.1-F4.6): 39 new files, 11 tables, 32 connector types; some already built (Phase 1 complete) | Decision | — | — | docs/MYOS.md, MyOS_Functional_Specification.md, MyOS_Technical_Specification.md | Which MyOS Phase 2/3 features survive? Which get replaced by HaseebOS equivalents?
SUMMARY: 29 implementation gaps + 6 TMCAI-ahead areas + 5 open questions = 40 total items ¦ Status: 8 MISSING, 12 PARTIAL, 6 TMCAI AHEAD, 1 MISLABEL, 2 Net New category ¦ P0 Critical: 10, P1 High: 9, P2 Medium: 7

## Implementation Phases
IMPLEMENTATION PHASES: Sequenced Rollout Plan
# | Phase | Gaps Addressed | Duration | Team Size | Deliverables | Success Criteria
1 | Phase 0: Foundation | G28 Redis, G1 Pub/Sub, G43 Env Config, G42 Feature Flags | 3-4 weeks | 2 backend | Redis Memorystore provisioned + connected; 4 Pub/Sub topics + DLQs created; feature flag gates for all new features; env config updated | Redis ping < 5ms; Pub/Sub publish-subscribe roundtrip < 500ms; all feature flags default OFF
2 | Phase 1A: Agent Framework | G2 ADK Agents, G3 Tool Taxonomy | 4-6 weeks | 2 backend + 1 GCP | 7 agents registered with base prompts; Brain Orchestrator dispatches to workers; tenant-scoped execution; Cloud Run agent worker deployed | Brain routes query to correct worker agent; tenant isolation verified; agent latency < 10s per turn
3 | Phase 1B: Feed Layer | G5 Feed Ingestion, G6 Open Items Scoring, G7 Archetypes, G8 Entity Alignment | 3-4 weeks | 2 backend | Connectors emit to feed.raw; feed_events table with dedup; open items scored with archetypes; entity names aligned | Zero duplicate events per content_hash; archetype classification accuracy > 90%; all entities mapped to spec names
4 | Phase 2A: Actions & Safety | G9 Risk Gating, G10 Action Handlers (priority 15), G11 Idempotency, G12 Kill Switch, G14 Circuit Breakers | 5-6 weeks | 3 backend + 1 frontend | Risk gating operational; 15 priority action handlers live; Redis SETNX idempotency; kill switch with 30s SLA; circuit breakers on all adapters | Kill switch halts all agents < 30s; zero duplicate executions; risk gating correctly classifies LOW/MED/HIGH
5 | Phase 2B: Remaining Actions & Undo | G10 (remaining 20 handlers), G13 Cascading Undo | 4-5 weeks | 2 backend + 1 frontend | All 35 action handlers; cascading undo with dependency graph; Action Undo UI | Undo chain correctly reverses all downstream actions; all 35 handlers execute with idempotency
6 | Phase 3A: Decision Intelligence | G15 Decision Log (3-layer), G16 Shadowing, G18 Morning Brief Audit | 4-5 weeks | 2 backend + 1 data | BQ decision archive operational; shadow scoring with golden dataset gate; morning brief aligned to 10 sections | BQ CDC < 60s latency; shadow scores meet thresholds (95% LOW, 98% MED); brief runs 06:00 PKT daily
7 | Phase 3B: Steering Wheel UI | G19 Steering Wheel, G20 KPI Dashboard, G21 Kill Switch UI, G22 Risk Queue, G23 Decision Viewer | 4-5 weeks | 1 backend + 2 frontend | Unified 5-tab Steering Wheel; KPI dashboard with trends; kill switch toggle; risk approval queue; decision log viewer | All 5 tabs functional; KPIs update in real-time; approval queue processes actions correctly
8 | Phase 4: Hardening & Ops | G24 Cloud SQL HA, G25 Envelope Encryption, G26 Data Residency, G27 Retention, G29 Monitoring, G4 Trace IDs, G17 Memory Bank | 4-6 weeks | 1 backend + 1 DevOps | Cloud SQL HA + PgBouncer; KMS encryption live; 4-region routing; retention tiers; monitoring dashboard + alerts; global trace IDs | Zero data loss on failover; all PII encrypted at rest; retention policies enforced; alert response < 5 min
9 | Phase 5: Polish & Scale | G19 cont. (15 embedded execution interfaces), remaining UI polish, load testing, security audit | 3-4 weeks | Full team | 15 embedded action interfaces; load tested to 100 concurrent tenants; security audit passed; documentation complete | P95 response time < 5s under load; zero critical security findings; all docs updated
TOTAL TIMELINE: ~30-41 weeks (7-10 months) ¦ Peak team: 3 backend + 2 frontend + 1 DevOps + 1 data ¦ Phase 0-2A are blocking; Phase 3+ can partially parallelize

## Source Traceability
SOURCE TRACEABILITY: Which Analysis Contributed What
# | Gap/Item | VSCode Analysis | Cowork Analysis | Merged Contribution
G1 | Pub/Sub Event Bus | ✓ Identified (G1); exact code refs (server.ts:16-49) | ✓ Identified; GCP topic config + DLQ specs + cost estimate ($40-135/mo) | VSCode: code precision; Cowork: infra specs
G2 | ADK Agent Framework | ✓ Identified (G2); detailed current state of all 4 agent files | ✓ Identified; Cloud Run worker service design + tenant scoping | VSCode: current architecture; Cowork: target architecture
G3-G4 | Tool Taxonomy + Trace IDs | ✓ Both identified (G20, G11); code refs | ✓ Both in gap analysis doc | VSCode more detailed on current state
G5-G8 | Feed + Open Items Layer | ✓ G6 archetypes, G16 entity naming | ✓ Feed ingestion service design; scoring extensions; feed_events table | Cowork added feed ingestion as distinct gap; VSCode had entity detail
G9-G14 | Actions Layer (6 gaps) | ✓ G3 idempotency, G6 handlers, G7 breakers, G8 kill switch, G9 undo | ✓ All 6; added risk gating as explicit gap; Redis key patterns; approval workflow | Cowork separated risk gating as own gap; both cover undo/kill switch
G15-G18 | Decision & Intelligence | ✓ G4 decision log, G5 shadowing, G18 morning brief, G19 memory | ✓ Decision log + shadowing + steering KPIs | VSCode: precise current state of each service; Cowork: BQ architecture
G19-G23 | UI (5 gaps) | ✓ G10 Steering Wheel with tab mapping | ✓ All 5 UI gaps; specific component names (KPICard, TrendChart) | Cowork broke UI into 5 specific gaps vs VSCode's single G10
G24-G29 | Infra & Security | ✓ G12 Cloud SQL, G13 encryption, G14 residency, G15 retention | ✓ All + Redis infra + monitoring; cost estimates per service | Cowork added Redis + monitoring as explicit gaps; both cover encryption/residency
G30-G35 | TMCAI Ahead (6 areas) | Not covered (focused on gaps only) | ✓ All 6: multi-tenant, multi-AI, PII, RAG, connectors, marketplace | Unique to Cowork analysis
Q1-Q5 | Open Questions | ✓ 4 questions (naming, WhatsApp, vector, user agents) | Not raised (assumed decisions already made) | Unique to VSCode analysis; added Q5 MyOS roadmap alignment
— | MyOS Feature Roadmap | ✓ Full 3-phase plan (F1.1-F4.6); 39 files; 11 tables; Phase 1 status | Not covered (didn't have MyOS spec documents) | Unique to VSCode analysis
— | Storage Strategy (File vs DB) | Not covered | ✓ Full 19-category analysis with per-item pros/cons | Unique to Cowork analysis
— | GCP Cost Estimates | Not covered | ✓ Per-service monthly cost ($270-1,115/mo total) | Unique to Cowork analysis
— | Implementation Phases | Proposed 3-step next (review→plan→test plan) | ✓ 43 codebase items + 17 GDrive docs + 25 GCP resources with priorities | Cowork more actionable; VSCode more review-oriented